TED UNIVERSITY

CMPE 492 Senior Design Project II

# BioAuth TODO and Backlog

Version 1 | 15 October 2026 | First delivery: 16 October 2026

This backlog translates the BioAuth V2 low-level design into implementation and verification work. The existing public website is an earlier prototype. Actual backend completion and individual ownership have not been confirmed; implementation items are therefore recorded as Planned, and ownership is expressed as a proposed role. Team assignment and effort estimates are set during sprint planning.

## Status and planning conventions

Planned: work is specified but completion is unverified. Review: a deliverable is prepared and awaits team/advisor review. Deferred: excluded from the initial implementation. Priority P0 blocks correctness or the first working verification; P1 supports evaluation and delivery; P2 is an extension. Dates below are proposed internal targets except the course deadlines.

| Milestone | Date | Exit condition |
| --- | --- | --- |
| LLD v1 and Backlog v1 | 16 Oct 2026 | Team review, PDF delivery and project-site publication. |
| LLD v2 and Backlog update | 23 Oct 2026 | Advisor feedback incorporated and scope changes recorded. |
| Working core and enrollment | 6 Nov 2026 | Real evidence contracts, physiological gate and review activation work. |
| Fusion and live integration | 19 Nov 2026 | L1/C-Q/L2 and authorized event flow execute on real inputs. |
| Test Plan and Backlog | 20 Nov 2026 | Test procedures, splits, responsibilities and denominators approved. |
| Frozen evaluation profile | 11 Dec 2026 | Thresholds/models fixed before final test; L3 assessed if data supports it. |
| Final report and Backlog | 31 Dec 2026 | Measured results, limitations, reproducible installation and updated documentation. |
| Demo | 4–17 Jan 2027, TBA | Recorded/live demonstration materials ready for announced date. |

## Required delivery actions

For LLD: upload the PDF to LMS, email the supervisor and jury, complete the coordinator form and publish the report on the project site. Publish the backlog version on the site. These submission actions remain team tasks; preparing these files does not perform submission.

# Implementation foundation

## B01 Review LLD v1 and six accepted decisions

P0 | Review | Target: 16 Oct | Proposed owner: Design lead / team | Depends on: None

Done when: Confirm rPPG gate, template provenance, statuses, review guard, C-Q and reporting.

## B02 Submit LLD and Backlog and update report links

P0 | Planned | Target: 16 Oct | Proposed owner: Delivery owner | Depends on: B01

Done when: All syllabus destinations completed; public links tested.

## B03 Record advisor feedback and issue LLD v2

P0 | Planned | Target: 23 Oct | Proposed owner: Design lead | Depends on: B01

Done when: Resolve Android deferral and timing feasibility; revised decisions traceable.

## B04 Create reproducible repository and service skeleton

P0 | Planned | Target: 23 Oct | Proposed owner: Platform role | Depends on: B01

Done when: Clean clone starts web/API/DB; migrations and test runner operate.

## B05 Implement evidence and decision contracts

P0 | Planned | Target: 23 Oct | Proposed owner: Core role | Depends on: B01

Done when: Statuses, null values, score direction and version validation tested.

## B06 Select model artifacts and record licenses

P0 | Planned | Target: 23 Oct | Proposed owner: CV role | Depends on: B01

Done when: Weight hashes, preprocessing and usage conditions in manifests.

## B07 Build session lifecycle and authenticated routes

P0 | Planned | Target: 30 Oct | Proposed owner: Backend role | Depends on: B04,B05

Done when: Ownership, expiry, finalize idempotency and terminal states tested.

## B08 Implement SDK capture and bounded transport

P0 | Planned | Target: 30 Oct | Proposed owner: Frontend role | Depends on: B07

Done when: Actual FPS/gaps/drop counts recorded; camera stop and disconnect handled.

## B09 Implement landmarks, ROI and input quality

P0 | Planned | Target: 30 Oct | Proposed owner: CV role | Depends on: B06,B08

Done when: Single-face windows and stable bounded ROIs; quality guidance emitted.

## B10 Implement face comparison and template storage

P0 | Planned | Target: 6 Nov | Proposed owner: CV/backend roles | Depends on: B05,B06,B09

Done when: Compatible embedding comparison; encrypted inactive/active templates; no client exposure.

# Verification and integration

## B11 Implement Visual PAD adapter and aggregation

P0 | Planned | Target: 6 Nov | Proposed owner: CV role | Depends on: B06,B09

Done when: Real inference, exact preprocessing, video statistics and failure status tested.

## B12 Implement CHROM/POS and spectrum analysis

P0 | Planned | Target: 6 Nov | Proposed owner: Signal role | Depends on: B05,B09

Done when: Known-signal and eligible dataset checks; invalid windows return unavailable results.

## B13 Qualify capture transport and rPPG usability

P0 | Planned | Target: 13 Nov | Proposed owner: Signal/frontend roles | Depends on: B08,B12

Done when: Compare transported vs lossless signals; document duration, gaps and quality limits.

## B14 Implement enrollment and reviewer guards

P0 | Planned | Target: 6 Nov | Proposed owner: Backend role | Depends on: B07,B10,B11,B12

Done when: No activation without biometric ACCEPT and reviewer approval; stale cases fail.

## B15 Implement common safety gate and L1

P0 | Planned | Target: 13 Nov | Proposed owner: Core role | Depends on: B10,B11,B12

Done when: Missing rPPG never accepts; reliable rejection precedence and runtime errors tested.

## B16 Implement C-Q and L2 strategies

P0 | Planned | Target: 19 Nov | Proposed owner: Core/research roles | Depends on: B15

Done when: Shared gate preserved; reliability and pattern rules independently testable.

## B17 Bind verification to payout-change execution

P0 | Planned | Target: 19 Nov | Proposed owner: Backend role | Depends on: B07,B14,B15

Done when: Action digest, ownership and single-use result checked atomically.

## B18 Build user guidance and authorized admin views

P1 | Planned | Target: 19 Nov | Proposed owner: Frontend role | Depends on: B08,B14,B16

Done when: Real events displayed; review and research permissions separated.

## B19 Acquire datasets and controlled capture consent

P0 | Planned | Target: 30 Oct | Proposed owner: Research role | Depends on: B01

Done when: Access terms and retention recorded; fallback corpus plan if access denied.

## B20 Prepare Test Plan and split manifests

P0 | Planned | Target: 20 Nov | Proposed owner: QA/research roles | Depends on: B05,B19

Done when: Subject/source separation, IDs, procedures and metric denominators defined.

# Evaluation and delivery

## B21 Extract paired feature table and metrics

P1 | Planned | Target: 27 Nov | Proposed owner: Research role | Depends on: B11,B12,B16,B20

Done when: Same sample evidence for C/C-Q/D; all outcomes and failures counted.

## B22 Train and assess L3 advisor

P1 | Planned | Target: 4 Dec | Proposed owner: Research role | Depends on: B21

Done when: Train-only fitting, validation calibration and unchanged safety constraints.

## B23 Freeze profiles and run blind evaluation

P0 | Planned | Target: 11 Dec | Proposed owner: QA/research roles | Depends on: B13,B20,B21

Done when: Models/thresholds frozen; paired results, coverage, errors and latency reported.

## B24 Security and privacy integration checks

P0 | Planned | Target: 11 Dec | Proposed owner: QA/backend roles | Depends on: B14,B17,B18

Done when: Cross-user access, override, double consumption and retention tests pass.

## B25 Update old public website for V2

P1 | Planned | Target: 18 Dec | Proposed owner: Frontend/content roles | Depends on: B03,B18

Done when: Remove obsolete claims and simulation ambiguity; correct repository/report links.

## B26 Package Core and SDK and validate clean install

P1 | Planned | Target: 18 Dec | Proposed owner: Platform role | Depends on: B06,B23,B24

Done when: Reproducible build, documentation and no sensitive data; publication rights checked.

## B27 Prepare final report and demo evidence

P0 | Planned | Target: 31 Dec | Proposed owner: Team / delivery role | Depends on: B23,B24,B26

Done when: Report actual results and limitations; all test outcomes traceable.

## B28 Dynamic light challenge experiment

P2 | Deferred | Target: Future phase | Proposed owner: Research role | Depends on: Core evaluation

Done when: Separate capture protocol and rPPG interference evaluation.

## B29 Native capture and deep-rPPG comparisons

P2 | Deferred | Target: Future phase | Proposed owner: Mobile/research roles | Depends on: Core evaluation

Done when: Separate scoped design and resources approved.

# Dependencies and risks

| Risk or dependency | Response and review trigger |
| --- | --- |
| Dataset approval is delayed | Start permission requests early; use consented controlled recordings for matched features without overstating sample diversity. |
| Short capture cannot yield usable rPPG | Measure duration/quality trade-off. Keep mandatory rPPG gate; submit justified timing change rather than silently accepting without it. |
| PAD baseline misses new attacks | Report species-specific failure; evaluate model adaptation on training/validation data only. |
| Transport degrades RGB signal | Qualify encoding against lossless input and revise capture profile before final comparison. |
| Work exceeds team capacity | Preserve core, safety gates and C-Q/L2 research. Keep optical/native/deep-rPPG deferred; review L3 scheduling explicitly. |
| Model weights cannot be redistributed | Use permitted artifacts and documented retrieval; do not bundle unapproved weights or datasets. |
| Pending review retains sensitive material | Enforce encrypted temporary storage, reviewer-only access and automatic expiry/deletion. |
| Old website misrepresents implementation | Clearly label simulation and update content/report links as each delivery is completed. |

## Weekly update procedure

At each team meeting, confirm individual owners, status, blockers and completion evidence. Move an item to Complete only with a linked commit, test result or reviewed deliverable. Re-estimate remaining work and preserve each dated backlog version. Course deadlines take precedence over proposed internal targets.

## Source and scope

Sources: CMPE 492 Syllabus New.pdf; BioAuth V2 Design Baseline v2.0; BioAuth Low Level Design Report v1. The backlog includes the accepted design clarifications from the preparation session. Individual team assignments and completed implementation are not inferred from the earlier simulation website.